## Charter
Engineering Information | [11 empty] | TRL | TRL Description | Term | Mean | Marketing Road map | Forcasting | 1 | Jan | 2023 | REF
To | Project Manager , Team Leader | [7 empty] | Date | 2023-01-10 |  | 1 | basic principles observed | Long Term | max 3 Yrs development time | R&T Roadmap | Scoping | 2 | Feb | 2024 | WM
Cc | Project Team | [7 empty] | PIC | sherif |  | 2 | technology concept formulated | Med Term | max 2 Yrs development time |  | Ideation | 3 | Mar | 2025 | AC
Re | IOT Charter | [10 empty] | 3 | experimental proof of concept | Short Term | max 1 Yrs development time |  | Roadmap | 4 | Apr | 2026 | SHA
[12 empty] | 4 | technology validated in lab |  |  |  | Conceptual Research | 5 | May | 2027 | WH
| Github_ID | IOT_2023OCT21 | [9 empty] | 5 | technology validated in relevant environment |  |  |  | Experimental Research | 6 | Jun | 2028 | Cross_Cutting
[12 empty] | 6 | technology demonstrated in relevant environment |  |  |  | Detail Design | 7 | Jul | 2029
| Project Data | [10 empty] | 7 | system prototype demonstration in operational environment |  |  |  | Subsystem / Application | 8 | Aug | 2030
|  | 3rd Exp Code |  | RD0000545 | [7 empty] | 8 | system complete and qualified |  |  |  | Shadwing | 9 | Sep | 2031
|  | 3rd Exp Description |  | IOT | [7 empty] | 9 | actual system proven in operational environment |  |  |  |  | 10 | Oct | 2032
|  | GROUP |  | Cross_Cutting
|  | Based Technology | [15 empty] | 11 | Nov | 2033
|  | TRL |  | 9 | actual system proven in operational environment | [12 empty] | 12 | Dec | 2034
|  | Project Cat. |  | Long Term | max 3 Yrs development time | [12 empty] | 13 |  | 2035
|  | Road_Map_Type |  | Marketing Road map | [13 empty] | 14 |  | 2036 |  | M
|  | Project Current Phase |  | Detail Design | [13 empty] | 15 |  | 2037
|  | Project Strt |  | Day | 21 | Month | Oct | Year | 2023 | [8 empty] | 16 |  | 2038
|  | Project End |  | Day | 21 | Month | Dec | Year | 2024 | [8 empty] | 17 |  | 2039
|  | Technology Group Mgr |  | ENG:Abdelrahman ELAraby | [13 empty] | 18 |  | 2040
|  | SW Team Leader |  | Eng:sherif Elgiar | [13 empty] | 19 |  | 2041
|  | Project Manager |  | Eng:sherif Elgiar | [13 empty] | 20 |  | 2042
|  | Project Team |  | ID Group | Member 1 |  |  | Member 2 | [9 empty] | 21 |  | 2043
|  |  |  | Prod. Dev. G | Member 1 |  |  | Member 2 | [9 empty] | 22 |  | 2044
|  |  |  | Comp. Dev. G | Member 1 |  |  | Member 2 | [9 empty] | 23 |  | 2045
|  |  |  | R&T Mech. G | Omar |  |  | Ahmed | [9 empty] | 24 |  | 2046
|  |  |  | R&T H.W. G | Member 1 |  |  | Member 2 | [9 empty] | 25 |  | 2047
|  |  |  | R&T S.W. G | Member 1 |  |  | Member 2 | [9 empty] | 26 |  | 2048
[18 empty] | 27 |  | 2049
|  | Software_Tasks | [15 empty] | 28 |  | 2050
|  |  | N | Task |  |  | Duration | Strt | Stop | PIC | STD Days | [6 empty] | 29
|  |  | 1 | Initiation | [13 empty] | 30
|  |  | 1.1 | Receive Requirements |  |  | 1 | 2023-10-21 | 2023-10-22 | Ahmed | 1 | [6 empty] | 31
|  |  | 1.2 | Data Analysis |  |  | 2 | 2023-10-22 | 2023-10-24 | Ahmed | 2
|  |  | 1.3 | Simulator Design |  |  | 1 | 2023-10-24 | 2023-10-25 | Ahmed | 1
|  |  | 1.4 | Paragmetic Design |  |  | 1 | 2023-10-25 | 2023-10-26 | Ahmed | 1
|  |  | 2 | Development
|  |  | 2.1 | MCAL
|  |  | 2.1.1 | MCAL Development |  |  | 14 | 2023-10-29 | 2023-11-16 | Ahmed | 14
|  |  | 2.1.2 | White Box Testing |  |  | 6 | 2023-11-16 | 2023-11-23 | Ahmed | 6
|  |  | 2.2 | HAL
|  |  | 2.2.1 | HAL Development |  |  | 14 | 2023-11-29 | 2023-11-16 | Ahmed | 21
|  |  | 2.2.2 | White Box Testing |  |  | 6 | 2023-11-16 | 2023-11-23 | Ahmed | 6
|  |  | 2.3 | Middleware
|  |  | 2.3.1 | Middleware Development |  |  | 3 | 2023-11-12 | 2023-11-15 | Ahmed | 3
|  |  | 2.3.2 | White Box Testing |  |  | 1 | 2023-11-15 | 2023-11-16 | Ahmed | 1
|  |  | 3 | APP
|  |  | 3.1 | Black Box Testing |  |  | 3 | 2023-11-19 | 2023-11-22 | Ahmed | 3
|  |  | 3.2 | Documentation |  |  | 1 | 2023-11-22 | 2023-11-23 | Ahmed | 1
|  |  | Phase | Planned | Actual
|  |  | 1 | 12 weeks
|  |  | 2 | 3 weeks
Documents
|  | Circuit | 2_Circuit
|  | Datasheet | 3_Data_sheet
|  | Simulator | 4_Simulator
|  | Source_Code | 5_Source_Code
|  | Flash_Code | 6_Flash_Code
|  | Refrences | 7_Refrences
ELARABY GROUP

## 1.1_Receive Requirements
Engineering Information
To | Project Manager , Team Leader | [7 empty] | Date | 2023-01-10
Cc | Project Team | [7 empty] | PIC | sherif
Re | IOT Receive Requirements
| Block Diagram |  |  |  |  | MIDDLEWARE
| I/P |  |  | HAL |  | I/P |  | HAL |  | O/P
| power reading |  |  |  |  | IOT_SET |  |  |  | send data to esp
| status |  |  |  |  | IOT_UPDATE
system error
Processing
O/P
System_State_Machine
1_State_Machine\State_Machine.vsdx
Pin Assignment
|  |  |  | 1 | P40/Tool0 | P120/AN19 | 32
|  | x |  | 2 | RESET | P0/INT8/AN17 | 31 | TXD1
|  |  |  | 3 | P137/INT0 | P1/INT10/AN16 | 30 | RXD1
|  |  |  | 4 | P122/X2 | P20/AN0 | 29
|  |  |  | 5 | P121/X1 | P21/AN1 | 28
|  | x |  | 6 | REGC | P22/AN2 | 27
|  | GND |  | 7 | VSS | P23/AN3 | 26
|  | 3.3 Volt |  | 8 | VDD | P147/AN18 | 25
|  |  |  | 9 | P31/INT4 | P10/AN20 | 24
|  |  |  | 10 | P74 | P11/AN21 | 23
|  |  |  | 11 | P73 | P12/AN22 | 22
|  |  |  | 12 | P72/INT7 | P13/AN23 | 21
|  |  |  | 13 | P70/INT6 | P14/AN24 | 20
|  |  |  | 14 | P30/INT3 | P15 | 19
|  |  |  | 15 | P50/INT1 | P16/RX0 | 18
|  |  |  | 16 | P51/INT2 | P17/TX0 | 17
Renesas
R5F11BBCAFP
BOM
| Material |  | Description |  |  | Maker | Maker PN |  | Supplier |  | MCU Pin

## 1.2_Analog_Analysis
Engineering Information
To | Project Manager , Team Leader | [6 empty] | Date | 2023-01-10
Cc | Project Team | [6 empty] | PIC | sherif
Re | IOT Analog Analysis
Sensor Data
| Material |  | Description |  |  | Maker | Maker PN | Supplier
| Temp(ºC) | NTC(K) | R2K) | VS (V) | Vo(V) | Resolution | ADC
| 40 | 1 | 4 | 3.3 | 2.64 | 12 | 3276
| 39 | 2 |  |  | 2.2 |  | 2730
| 38 | 3 |  |  | 1.8857 |  | 2340
| 37 | 4 |  |  | 1.65 |  | 2048
| 36 | 5 |  |  | 1.4667 |  | 1820
| 35 | 6 |  |  | 1.32 |  | 1638
| 34 | 7 |  |  | 1.2 |  | 1489
| 33 | 8 |  |  | 1.1 |  | 1365
| 32 | 9 |  |  | 1.0154 |  | 1260
| 31 | 10 |  |  | 0.94286 |  | 1170
| 30 | 11 |  |  | 0.88 |  | 1092
| 29 | 12 |  |  | 0.825 |  | 1024
| 28 | 13 |  |  | 0.77647 |  | 963
ELARABY GROUP

## 1.2_Digital_Analysis
Engineering Information
To | Project Manager , Team Leader |  |  |  | Date | 2023-01-10
Cc | Project Team |  |  |  | PIC | sherif
Re | IOT Digital Analysis
Load Data
| Material | Description | Maker | Maker PN | Supplier
| Event |  |  | Circuit
Action
Notes
ELARABY GROUP

## 1.2_System Errors
Engineering Information
To | Project Manager , Team Leader |  |  | Date | 2023-01-10
Cc | Project Team |  |  | PIC | sherif
Re | IOT System Errors
ERRORS
| ERR No. | ERR Display | ERR Action
1
2
3
4
5
6
7
8
9
10
ELARABY GROUP

## 1.3_Simulator Design
Engineering Information
To | Project Manager , Team Leader | Date | 2023-01-10
Cc | Project Team | PIC | sherif
Re | IOT Simulator Design
Simulator Kit
|  | Design | Review
ELARABY GROUP

## 1.4_Static Design
Engineering Information
To | Project Manager , Team Leader | [7 empty] | Date | 2023-01-10
Cc | Project Team | [7 empty] | PIC | sherif | [6 empty] | Mode
Re | IOT Static Design | [9 empty] | Mode | States | I/P (HW/Config) | I/P Module | Processing | O/P (HW/Config) | Factory Default
[11 empty] | STOP | [5 empty] | Test
| HW | HW Names | Modules | Modules | HW | HW Names | Modules | Modules |  |  |  | OFF | OFF_PB | PB_Update | OFF_Update | EEPROM_Update | Stop
| I/P |  |  |  | O/P |  |  |  |  | Interfaces |  |  | End of operation | End of operation_Update |  | Load_Update | SLEEP
[10 empty] | Init |  |  | LVR | LVR_Update |  | LED_Update | RUN
[10 empty] | Set | [5 empty] | Buzzer_Update
[10 empty] | Get | Sleep
[10 empty] | Update |  | FAULT | ERR | ERR_Update | Fault_Update
Sys need to Sleep
[10 empty] | Strt | RUN
[10 empty] | Stop |  | WASH | Wash_PB | User_Program_Update
User_Program
[10 empty] | Enable |  |  | Water Level | Water_Level_Update
[10 empty] | Disable |  |  | Weight | Weight_Update
| Processing | HW Names | Modules | Modules | Modes | HW Names | Modules | Modules |  |  |  |  | Timer | Timer_Update
| Sys | uart | uart_Update | uart_Init | Modes | LVR | LVR_Update | LVR_Init |  |  |  | SOAK
[6 empty] | END | END_Update | END_Init |  |  |  | RINSE
[6 empty] | Fault | Fault_Update | Fault_Init |  |  |  | SPIN
[6 empty] | Test_Mode | Test_Mode_Update | Test_Mode_Init |  |  |  | TUB_CLEAN
[6 empty] | Factory_Deafult | Factory_Deafult_Update | Factory_Deafult_Init |  |  |  | Child_proof
TEST
Factory default
ELARABY GROUP
Note on U6: Sherif Abdelfatah Roshdy Elgiar: 1-Save data in eeprom 2-Off System
Note on T8: Sherif Abdelfatah Roshdy Elgiar: once voltage reach determined volt before selected reset volt

## 1.4_Dynamic Design
Engineering Information
To | Project Manager , Team Leader | [8 empty] | Date |  |  | 2023-01-10
Cc | Project Team | [8 empty] | PIC |  |  | sherif
Re | IOT Dynamic Design
Notes
| 1 | Tick time : 1msec for 8 Tasks (1Mhz) , so 16 Task (2Mhz) , 32 Task (4Mhz) & etc …
| 2 | Execution time have to be lower than tick time
| N | Task | Execution Time (msec) | Delay (msec) | Period (msec)
| 2 | iot_set |  | 0 | 5
| 1 | iot_update |  | 1 | 10
| 3 |  |  | 2 | 15
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
[6 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100
ELARABY GROUP | bar: 0 to 6

## 2.1.2_White Testing
Engineering Information | [14 empty] | Pass
To | Project Manager , Team Leader | [10 empty] | Date | 2023-01-10 |  | Fail
Cc | Project Team | [10 empty] | PIC | sherif
Re | White Box Testing
| Device | Driver | Write by | Test by | Format | STD | API | DTS Review | WDT Enable | Event | Action |  |  | Result
Circuit
Final Result
Approve
ELARABY GROUP

## 3.1_Black Testing
Engineering Information | [5 empty] | Pass
To | Project Manager , Team Leader |  | Date | 2023-01-10 |  | Fail
Cc | Project Team |  | PIC | sherif
Re | IOT Black Testing
Normal Mode
| Event | Action |  |  | Result
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
Fault Mode
| Event | Action |  |  | Result
1
2
3
4
5
6
7
8
9
10
Test Mode
| Event | Action |  |  | Result
1
2
3
4
EEPROM
| Event | Action |  |  | Result
1 | Data Saved incase User Off
2 | Data Saved incase Plug removed
3 | Data return to default after factory mode reset
Approve
ELARABY GROUP